NEW GRAIN MARKET, NAJAFGARH

| Sl.no. | Name of Work | Earnest Money | Name of party contract awarded | Estimated cost | Time of completion | Actual expenditure incurred | Date of actual completion |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | C/o Canteen at NGM Najafgarh | 13,200.00 | M/s D.K.K. Promoters & Builders | 5,27,283/- | 3 months | 5,38,640.48 | 15.4.2000. |
| 2. | C/o Temporary shed at NGM, Najafgarh. | 78,520.00 | M/s Satyavir Khatri & Sons | 31,40,570/- | 5 months | 26,83,287.96 | 29.4.2000. |
| 3. | Raising, providing WBM, premix in the idle truck parking area at NGM, Najafgarh. | 52,000.00 | M/s Satyavir Khatri & Sons | 20,75,027/- | 5 months | 26,46,889.00 | 1.12.2001. |
| 4. | Interior works at farmer’s Rest House/Administrator office at N GM, Najafgarh. | 45,300.00 | M/s R.P. Singh & Co. Pvt. Ltd. | 18,08,681/- | 3 months | 25,88,892.00 | 30.11.2001. |
| 5. | P/L BM & AC in the idle parking area at NGM Najafgarh. | 25,000.00 | M/s Capital Construction Co. | 9,87,196/- | 1 month | 14,20,805.00 | 27.3.03. |
| 6. | P/L cement concrete flooring for creating open auction platform at NGM, Najafgarh. | 19,500/- | M/s Satyavir Khatri & Sons. | 7,69,172/- | 2 months | 10,55,377.00 | 4.5.2002. |
| 7. | C/o two rooms for installation of water cooler and toilet block | 26,000/- | M/s Kay Ess Const. Co. | 10,31,475/- | 45 days | 12,61,796.00 | 10.12.2003. |

Fruit & Vegetable Market, Keshopur

| Sl.no. | Name of Work | Earnest Money | Name of party contract awarded | Estimated cost | Time of completion | Actual expenditure incurred | Date of actual completion |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Installation of 2 nos. of tube well | - | M/s Haryana State Minor Irregation Tubewell Corpn,. Ltd. Faridabad. | 3,30,460.00 | - | 304633/- | 26.12.88 |
| 2. | S/filling good earth Ph-I | 16920/- | M/s Manohar Lal Gupta & Co. Pvt. Ltd. | 8,46,000/- | 2 months | 700615.92 | 5.1.89 |
| 3. | Laying of services i.e. earth filling and c/o auction platform | 20,000/- | M/s Manohar Lal Gupta & Co. Pvt. Ltd. | 90,86,000/- | 12 months | 8315520.00 | 4.9.90 |
| 4. | C/o front boundary wall with MS grills & RCC culvert with MS grating. | 19,500/- | M/s Nathu Ram Gupta & Sons. | 7,78,525/- | 4 months | 1181500.00 | 30.9.91 |
| 5. | C/o Admn. block | 62744/- | M/s Babu Ram Gupta | 2509757/- | 18 months | 3485690/- | 15.6.92 |
| 6. | C/o informal sector , check post etc. | 11700/- | M/s JP Gupta | 467592/- | 6 months | 744970/- | 16.8.92 |
| 7. | C/o shops & Kiosks at informal sector-II | 12301/- | M/s Saroha Const. Co. | 492044/- | 8 months | 10,31,437/- | 15.3.96 |
| 8. | C/o informal Sector-I (part) | 34600/- | M/s DKK Promoters & Builders. | 1382574/- | 8 months | 15,49,203/- | 30.10.96 |
| 9. | C/o WBM road & laying of services | 28710/- | M/s DKK Promoters &Builders | 2542023/- | 4 months | 2451360.00 | 15.4.96 |
| 10. | C/o Entry, Exit offices & 12 nos. of water Huts. | 17220/- | M/s Saroha Const. Co. | 688792/- | 8 months | 1061421/- | 26.11.96 |
| 11. | P/L premix carpet surfacing in parking area. | 5900/- | M/s Satyavir Khatri & Sons. | 2,36,327/- | 30 days | 348109.18 | 19.2.97 |
| 12. | C/o 99 nos. wholesellers shops | 1,00,000/- | M/s H.P. Gupta | 21023602/- | 20 months | 3,81,84,906/- | 31.3.98 |
| 13. | P/L Fibre sheet over Vault of wholesellers shops | 1,00,000/- | M/s Fiberfill Engineers | 53,22,636/- | 4 months | 4657030/- | 25.9.98 |
| 14. | C/o 7 nos. dustbins (Dhalow) | 33625/- | M/s Saroha Const. Co. | 13,44,832/- | 3 months | 1592967.16 | 3.11.98 |
| 15. | C/o 107 nos. wholesellers shops | 1,00,000/- | M/s DKK Promoters & Builders | 51,48,896/- | 3 months | 8323125/- | 21.1.99 |
| 16. | C/oloading/unloading platform and laying BM/AC and water line for fire fighting system. | 1,00,000/- | M/s HR Builders | 13997885/- | 8 months | 15,49,203/- | 20.1.99 |
| 17. | C/o pump room & fixing of grills around ground water tank. | 22555/- | M/s DKK Promoters & Builders | 902060/- | 3 months | 1406914/- | 1.7.99 |
| 18. | P/fixing MS Grills around the park. | 22000 | M/s Kavenderveer Singh | 879995/- | 2 months | 1014453/- | 12.4.99 |
| 19. | C/o footpath alongwith sides of roads | 73850/- | M/s SS Builders | 2953655/- | 3 months | 2700263/47 | 1.1.99 |
| 20. | P/F FRP shelter on the beam of cutout portion, Trinagular |  | M/s Fibrefill Engineers |  | 20 days | 7,91,220/- | 26.11.99 |
| 21. | P/L CI water supplying line underground tank . | 8025/- | M/s DKK Promoters & Builders | 320936/- | 45 days | 350553/- | 3.7.2000 |
| 22. | P/L sewer line for connection of sulabh | 4525 | M/s Om Contracts | 159520/- | 2 months | 177459/- | 29.5.2000 |
| 23. | C/o Toilet on ground floor in Admn. block at F&V Keshopur. | 2275/- | M/s Surya Const. Co. | 90431/- | 2 months | 102840/- | 20.6.2000 |
| 24. | P/Fixing MS grills around green belt . | 4200/- | M/s Satyaveer Khatri & Sons. | 167867/- | 1 month | 232293/- | 30.9.2000 |
| 25. | Earth work and pre conditioning of ground for development of green belt. | 14216 | M/s R P Singh | 568650/- | 30 days | 456844.61 | 9.4.01 |
| 26. | P/L RCC pipe line for electrical cables | 8700/- | M/s Vinod Kumari | 347128/- | 2 months | 458072/- | 18.6.01 |
| 27. | Extn. of Admn. block (2 floors) | 70,000/- | M/s DKK Promoters & Builders | 2673417.00 | 6 months | 3945851/- | 11.9.01 |
| 28. | P/F Retro reflective over head sign board at entry and exit gate. | 17500/- | M/s Ravi & Co. Ltd. | 685151/- | 2 months | 387563/- | 14.9.2001 |
| 29. | C/o Urinal block in market. | 3900/- | M/s Arun Contracts | 154880/- | 11/2 months | 298461/- | 17.7.02 |
| 30. | C/o parking shed for staff cars and Govt. vehicles. | 12500/- | M/s Fiberfill Engineers | 490844/- | 2 months | 736322 | 6.2.03 |
| 31. | P/Layng and repairing kota stone flooring . | 11200/- | M/s Naresh Kumar | 4,44,687/- | 1 month | 345677/- | 31.3.04. |

FODDER MARKET AT MANGOLPURI

| Sl.no. | Name of Work | Earnest Money | Name of party contract awarded | Estimated cost | Time of completion | Actual expenditure incurred | Date of actual completion (Time period) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | S/F of earth at Fodder Market Mangolpuri. | 26700/- | M/s Varun Builders | 10,68,000/- | 60 days | 11,30,164/- | 20.4.88 |
| 2. | C/o Boundary wall alongwith anti climbing fencing | 23012/- | M/s Devender Kumar | 11,50,592/- | 120 days | 5,21,384/- | 16.10.88 |
| 3. | Development of New Fodder market Mangolpuri (C/o roads, laying of sewerline, waer line and strom water line) | 20,000/- | Nathu Ram Gupta & C. | 45,94,388/- | 9 month | 67,17,791/- | 31.3.92 |
| 4. | A/R and maintenance of New Fodder market Mangolpuri. | 812/- | M/s Satveer Khatri & Sons. | 32464/- | 30 days | 32609/- | 2.4.94 |
| 5. | Repairing and raising of boundry wall of New Fodder Market, Mangolpuri. | 10,400/- | M/s Arun Contracts. | 4,14,052/- | 2 months | 4,07,779/- | 18.6.98 |
| 6. | Annual repair and maintenance of Fodder Market, Mangolpuri. | 6800/- | M/s Puja Const. Co. | 2,71,722/- | 45 days | 3,69,612/- | 17.8.01 |
| 7. | P/F MS Main gate at Fodder Market, Mangolpuri. | 4500/- | M/s Puja Const. Co. | 1,79,241/- | 45 days | 2,61,787/- | 24.12.01 |
| 8. | C/o and renovation work in office of Chairman at Fodder Market Mangolpuri. | 13,500/- | M/s Puja Const. Co. | 5,24,106/- | 45 days | 8,49,058/- | 30.8.02 |
| 9. | C/o RCC U/G water tankat Fodder Markt Mangolpuri. | 19,300/- | M/s R.P. Singh & Co. P. Ltd. |  | 4 months | 7,70,000/- | 4.10.02 |
| 10. | C/o of twonos.check post at.Fodder,Mkt.,Mangolpuri. | 14,000/- | M/s Nareash Kumar | 5,59,139/-- | 60 days | 5,65,847/- | 24.12.02 |
| 11. | P/F water tank at FodderMarket,Mangolpuri. | 3400/- | M/s Vijender Bhardwaj | 1,33,824/- | 45 days | 320462/- | 21.4.03 |

NGM, NARELA

| Sl.no. | Name of Work | Earnest Money | Name of party contract awarded | Estimated cost | Time of completion | Actual expenditure incurred | Date of actual completion |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | C/o office building at NGM Narela. | 1,00,000/- | M/s Rama Const. Co. | 88,82,948/- | 15 months | 1,22,89,502.34 | 16.9.2003 |
| 2. | C/o office cubicals (Hospital block) at NGM Narela. | 1,00,000/- | M/s R.P. Singh & Co. Pvt. Ltd. | 64,14,784.55 | 9 months | 76,45,235.66 | 27.6.2003 |
| 3. | C/o Septic Tank (II) at NGM, Narela. | 31,425/- | M/s Saroha Const. Co. | 12,56,944.60 | 3 months | 14,21,021.00 | 22.9.2003 |
| 4. | C/o 5 nos. water booth including room for chillar plant and toilet block 2 nos. at NGM Narela. | 56,225/- | M/s Satveer Khatri & Sons | 22,48,837.00 | 2 months | 27,57,814.28 | 28.10.2003 |

ROHINI

| Sl.no. | Name of Work | Earnest Money | Name of party contract awarded | Estimated cost | Time of completion | Actual expenditure incurred | Date of actual completion |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Construction of DAMB staff quarters at Rohini. | 50,000/- | M/s B.K. Builders | 68,76,675/- | 18 months | 1,33,55,412/- | 6.11.1996 |

RAJENDRA PLACE, GUEST HOUSE

| Sl.no. | Name of Work | Earnest Money | Name of party contract awarded | Estimated cost | Time of completion | Actual expenditure incurred | Date of actual completion |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Supplying of chairs for Convention Centre cum Guest House at Rajendra Place. | Nil | M/s Chairs Gallery | L.S. | 8 days | 3,70,328/- | 28.2.01 |
| 2. | Establishment of Convention Centre cum Guest House at Rajendra Place Premises (Interior work) | 1,00,000/- | M/s Value Link Interior | 74,81,172/- | 4 months | 70,50,288/- | 31.12.2000 |

DAMB OFFICE BUILDING, JANAKPURI

| Sl.no. | Name of Work | Earnest Money | Name of party contract awarded | Estimated cost | Time of completion | Actual expenditure incurred | Date of actual completion (Time period) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | P/F partition, false ceiling, Misc. civil and electrical work (Part-I) at office building Janakpuri | 77910/- | M/s Nuelem Ltd. | 31,16,056/- | 10 days | 31,99,247/- | 6.6.98 |
| 2. | P/F partition false ceiling, misc. civil and electrical work (Part-II) at office building, Janakpuri, Delhi. | 58,600/- | M/s Design Tech. | 23,42,559/- | 75 days | 23,72,616/- | 9.6.98 |
| 3. | C/o office building including electrical, sanitation, and water supply installation in Institutional area, Pankha Road, Janakpuri. | 33,562/- | M/s Competent Construction Co. | 35,12,366/- | 18 months | 48,85,365/- | 26.11.96 |

FLOWER MARKET AT OKHLA

| Sl.no. | Name of Work | Earnest Money | Name of party contract awarded | Estimated cost | Time of completion | Actual expenditure incurred | Date of actual completion |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | C/o boundary wall and filling of good earth at Flower Market, Okhla. | 58.000/- | M/s Saroha Const. Co. | 23,10,776/- | 4 months | 30,84,138/- | 3.9.2001 |
| 2. | Const. of office building laying storm water line and WBM roads at Flower market, Okhla. | 45,000/- | M./s Pooja Const. Co. | 17,62,784/- | 4 months | 24,79,924/- | 30.7.02 |
| 3. | Const. of sheds in plot No. 277 at Flower Market, Okhla. | 54,500/- | M/s Fiberfill Engineers | 21,69,826/- | 4 months | 23,81,028/- | 21.6.02 |
| 4. | Const. of sheds, roads and laying SW line at Plot no. 278 in Flower market, Okhla. | 52,000/- | M/s Pooja Const. Co. | 20,78,242/- | 3 months | 17,94,343/- | 12.3.03 |
| 5. | P/F fibre sign board at front of shops | 8,100/- | M/s Fibrefill Engineers. | 3,20,266/- | 1 month | 2,66,530/- | 3.4.03 |
| 6. | P/F Retro-reflective over head sign board for Flower Market. | 6,500/- | M/s C.B.M. Industries Ltd. | 2,49,365/- | 1 month | 2,67,852/- | 30.5.03 |

Fodder Market, Tikri Kalan

| Sl.no. | Name of Work | Earnest Money | Name of party contract awarded | Estimated cost | Time of completion | Actual expenditure incurred | Date of actual completion (Time period) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | C/o Toilet at proposed Fodder market, Tikri Kalan. |  | M/sManas Bharti Foundation. | 2,06,500/- | 2 months | 2,47,715/- | 19.7.99 |
| 2. | Erection of Sereen at proposed market at Tikri Kalan. | 21,700/- | M/s Satyaveer Khatri & Sons. | 8,66,410/- | 2 months | 10,37,603/- | 5.5.99 |
| 3. | C/o Temporary shed at proposed Fodder Market Tikri kalan. | 27,800/- | M/s Jyoti Const. Co. | 11,10,334/- | 2 months | 23,99,825/- | 20.6.99 |
| 4. | C/o pavements with dry stone pitching at Tikri Kalan. | 24,000/- | M/s D.K. Promoters & Builders. | 9,59,594/- | 2 months | 12,05,894/- | 25.5.99 |
| 5. | P/L storm water drain and desilting of open surface drain at proposed Fodder market Tikri kalan. | 13,600/- | M/s Saroha Const. Co. | 5,43,684/- | 2 months | 7,18,715/- | 10.11.99 |
| 6. | Laying W.B.M. and premix carpeting at proposed Fodder Market, Tikri Kalan. | 19,200/- | M/s D.K.K. Promoters & Builders. | 7,65,000/- | 45 days | 5,65,433/- | 25.9.99 |
| 7. | P/L Fibre glass water storage tanks i/c covering with AC sheets at proposed Fodder Market, Tikri Kalan. | 4950/- | M/s Saroha Const. Co. | 1,96,136/- | 30 days | 2,04,510/- | 24.12.99 |
| 8. | Boring and installation of deep bore hand pump at proposed Fodder Market, Tikri Kalan. |  | M/s Arun Contracts. | 5,39,50/- | 30 days | 53,950/- | 13.11.99 |
| 9. | Installation of tubewell at proposed Fodder market, Tikri Kalan (2 nos.) |  | M/s MITC Gurgaon | 3,00,506/- | 2 months | 3,0,506/- | 28.8.00 |
| 10 | C/o tubewell room and laying GI water supply line at proposed Fodder Market Tikri Kalan. | 7600/- | M/s Arun Contracts | 3,030,390/- | 2 months | 1,54,594/- | 13.5.00 |
| 11. | P/ maintenance of creepers plants. | 2300/- | M/s Agastya Flora inc. | 91,296/- | 1 month | 1,57,200/- | 25.6.01. |